## HRMS
HRMS
SR | Module | Work Details | Timeline | Status | Remarks
1 | Manage Employee | Employee,award,promotion,transfer,terminate,resignation, warnings, complaints, employee view profile, leave heads, calendar | 10 days | Done
2 | Manage Attendance | mark attendance, attendance reports, holiday calendar | 5 days | Done
3 | Mange Payroll | leave management, salary, bonus, reimbursement, investment, EPF, ESI, TDS taxes | 18 days | Working | investments, pay run
4 | HRMS Settings | payhead, statutory,salary template, tax master,department, leave heads,working day shift policy | 12 days | Done
5 | Account Management | Employee Panel and Other admin HR etc | 5 days | Pending
6 | Role and Permission |  | 1 days | Done
Start Date | January Last week 2025

## Worksheet
Worksheet
Date | Module | Work | Status | Remark
2025-04-07 | Payroll | work on employee panel, reimbursement, reimbursement in admin panel and to salary | Done
2025-04-08 | Payroll | Bonus import and listing, bonus add and calculate in salary | Done
2025-04-09 | Payroll | Investment, work on design, 2hr meeting with Vishal Sir for how to implement investment | Working
2025-04-10 | Payroll | master in superadmin, investment types according to 80c and other loans, rents with financial year | Working
2025-04-11 | Payroll | investment details save in database implements in , admin approvel, implements in salary
2025-04-14 | Payroll | pay run with bulk salary pay, create manual and auto pay run